## Slide 1: Project Kick-off
[AGILE tip: Drop this file’s link into your meeting’s chat and link it in your PM tool]
Project name ¦ date

## Slide 2: Agenda
Introductions [list attendees + their roles on this agenda slide]
Project summary [see visual project brief + next slide]
Learning design
Project timeline | Project management
Q&A
Next steps + action items | dates

## Slide 3: Project Brief | How to give and receive feedback
Project Summary
Create two asynchronous eLearning courses for: 1) How to give feedback and 2) How to receive feedback Each course will address managers’ request for more training on giving/receiving FB. Each course will include one leader video and one downloadable job aid. Target audience: Line managers levels III-VI. Global audience Duration ¦ tools: 20 min each; Rise |  | Managers will learn how to comfortably and effectively give and receive feedback. Learner experience: Learners will take two, 20-minute Articulate Rise courses with leader video and content interactions. At the end of each course, they will complete a ‘feedback scenario’ to assess their new knowledge. Content map: Feedback courses
Measurement ¦ KPI: Train 75% of all managers III-VI by EOY FY2023 |  | 
Stakeholders: Jose Becerra, Vivian Lu |  | 
Desired Performance Outcomes
Content (13 min)
Leader video (2 min)
Scenario
(5 min)
Job aid

## Slide 4: Learning Design
[Note: You may know the answers to some of these questions - choose which you need]
Are there specific branding/ look and feel guidelines that we need to adhere to?
What type of accessibility should be included in this learning experience? Cite examples
Will there be any additional reviewers, such as SMEs, for this project?
What kind of assessments would you like to incorporate in the course?
Are there any other cross-functional team members/stakeholders that will be involved in the project who are not present, such as in-house video production or graphic design?
What is the tone and ‘voice’ for this project?
We use [insert example of completed design doc] these formats to communicate written and visual course information. Is there anything else you’d like to see included?”
What is a realistic review period throughout design and development for your stakeholders? One week, two? (Note here that they will have two reviews for the design document/storyboard, and two review rounds for alpha and beta, and that the reviews may be chunked into smaller parcels
Are there any things we need to know about LMS or LRS integration for the course design/launch?
I know it’s early, but what kind of evaluation procedures might be put into place? Thoughts surrounding a pre-test that needs to be delivered ahead of training? In-course feedback? Post-course feedback?

## Slide 5: Project Timeline
[remember, this is your “10,000 foot view” - major milestones/ID process only - see example]
Analyze
Analyze content
Develop learning objectives. Create content map and high-level content outline for course and job aid. One review cycle.
Design storyboard
Storyboard or design document will show course language, images, graphics, interactions, video script, and assessments. One review cycle.
Design
Develop prototypes
Development will include two review stages: first (alpha) prototype, and second (beta) prototype of course in chosen tool. Will include video review. Two review cycles.
Develop
Use feedback to iterate
Feedback will start with pilot launch, and continue as long as the course is running. Cycles of FB review will be establish for continued course improvement. Ongoing scheduled reviews and updates.
Evaluate
Pilot launch / full launch
After all course iterations, the final version of the course will be implemented to a small ‘test; group for feedback. Necessary changes will be made before full target audience launch. One review cycle.
Launch
3/30 - 4/15 | 4/18 - 5/18 | 5/21 - 6/21 | 6/25 - 7/15 LAUNCH: 8/1 | 1st look at FB: 8/20

## Slide 6: Our project plan
[insert link to shared task-level project plan (Asana, Google Sheets, etc) and briefly review milestones]

## Slide 7: Q&A
[Remember to allow 5-10 mins for stakeholder-driven Q&A and input]

## Slide 8: Next steps | Action items
Learning design next steps:
[who/what] | Due by:
Other team members’ next steps
[who/what] | Due by:

## Slide 9: Let’s get started!
[Last slide - add team email addresses + optional motivational image]